## Sheet1
Segment/section | Str no. | DTC | Protus Name | Status (O/C) | start data and time | End date and time | Owner | Status | Description | Ageing | Status
HD | 277A | P0305, P0274, P0300 | VE2188_TT-Endurance-B-0078 | C | 2023-05-27 | 2024-07-21 | Ashish Kumar Paroha | Validation Closed | Pro 8055TT_CNG_LNG_ Poor pick and misfiring accelerator not going above 1200 rpm | 421 | Close
HD | 277A | B0379 | VE2188-Endurance-B-0379 | C | 2023-06-26 | 2024-09-05 | Ashish Kumar Paroha | Validation Closed | Protus_Pro 8055TT_CNG_LNG_Poor pick up_Jerks & 5th cylinder misfiring issue_P0305 Active code | 437 | Close
HD | 277B | B0079 | VE2188_TT-Endurance-B-0079 | O | 2024-04-04 |  | Ashish Kumar Paroha | Verification | Protus_Pro 6055TT_CNG_LNG_Engine oil throw from turbocharger which abnormal noise and white smoke | Open | Open
HD | 277B | NA | VE2188_TT-PerformanceAndFeatureVerification-B-0002 | P | 2023-11-30 |  | R V BIBIN | Verification | Pro6055TT LNG gradeability not meeting the requirement | In process | In process
HD | 277A | NA | VE2188_TT-PerformanceAndFeatureVerification-B-0001 | P | 2023-11-30 |  | R V BIBIN | Verification | Pro6055TT LNG acceleration trial not meeting | In process | In process
SCV | MC2JACRC0REB00009 | U1C019A | Protus_TITAN_CSE_009_ DTC U1C019A BCS CAN message timeout | P | 2024-11-13 |  | Ramakant Pandey | Roadmap for DR/PM | BCS CAN message timeout | In process | In process
SCV | MC2JACRC0PC524712 | NA | VE1430-Endurance-B-0009 | C | 2023-07-07 | 2024-10-21 | Akshay khalkar | Closure | Built Maturity : Base engine : Engine oil leakages from engine, coolant mixed with engine oil | 472 | Close
EV | MC2V2RRT0PH101418 | NA | 12m EV Staff Bus-Endurance-P-0007 | C | 2023-11-24 | 2024-11-28 | Rahul Verma | Validation Closed | Squeak noise from RH side Hatrack | 370 | Close
EV | MC2V2RRT0PH101418 | NA | 12m EV Staff Bus-Endurance-B-0004 | P | 2024-02-14 |  | Ramanand Pawale | Verification | 12M EV Staff AC bus_V1_ Quality_ Grease leakage from front axle LHS wheel end | In process | In process
LMD | 496 | NA | VE3363-Endurance-B-0003 | P | 2024-04-12 |  | Subodha Nayak | Part Avaibility | Rear RHS shock absorber failure | In process | In process
LMD | 642 | NA | VE3361-PerformanceAndFeatureVerification-B-0006 | C | 2024-07-25 | 2024-11-27 | Chetna Kanodiya | Validation Closed | B8F Muel_Performance and Feature_Compressed air Static noise (Service brake ) not Meeting | 125 | Close
LMD | 934 | NA | VE3325-Export Validation-C-0019 | P | 2024-08-26 |  | Sakti Prasad Sarangi | Verification | Pro 3009 H EIII E494 24V NAC 36S SAF_RHD_Vehicle skidding & Juddering issue observed while applying brake at 60 kmph | In process | In process
BUS | 400 | NA | VE3330-Export Validation-C-0024 | P | 2022-01-13 |  | Rahul Verma | ECO Implementation | Several issue observed from Bus body (Design) (ORVM vibration , air from floor etc) | In process | In process
BUS | 978 | NA | VE3191_PROTUS-AET-B-0015 | C | 2018-10-12 | 2019-11-06 | Abhoy Chandra | Validation Closed | Critical gap between rear spring rear end cotter bolt and battery. | 390 | Close