## Sheet1
Segment/section | Str no. | DTC | Protus Name | Status (O/C) | start data and time | End date and time | Owner | Status | Description
EV | MC2V2RRT0PH101418 | Not available | 12m EV Staff Bus-Endurance-B-0004 | O | 2024-02-14 | Not available | Ramanand Pawale | Verification | 12M EV Staff AC bus_V1_ Quality_ Grease leakage from front axle LHS wheel end
LMD | Not available | Not available | VE3363-Endurance-B-0003 | O | 2024-04-12 | Not available | Subodha Nayak | Part Avaibility | Rear RHS shock absorber failure
LMD | Not available | Not available | VE3361-PerformanceAndFeatureVerification-B-0006 | C | 2024-07-25 | 2024-11-27 | Chetna Kanodiya | Validation Closed | B8F Muel_Performance and Feature_Compressed air Static noise (Service brake ) not Meeting
LMD | Not available | Not available | VE3325-Export Validation-C-0019 | O | 2024-08-26 | Not available | Sakti Prasad Sarangi | Verification | Pro 3009 H EIII E494 24V NAC 36S SAF_RHD_Vehicle skidding & Juddering issue observed while applying brake at 60 kmph
BUS | Not available | Not available | VE3330-Export Validation-C-0024 | O | 2022-01-13 | Not available | Rahul Verma | ECO Implementation | Several issue observed from Bus body (Design) (ORVM vibration , air from floor etc)
BUS | Not available | Not available | VE3191_PROTUS-AET-B-0015 | C | 2018-10-12 | 2019-11-06 | Abhoy Chandra | Validation Closed | Critical gap between rear spring rear end cotter bolt and battery.